## Slide 1
Week 4
Progress Report
HE Toolkit Dashboard | 21-27 June + Recent GitHub Updates
Monday Meeting with Professor Ruzanna
Core theme
From clarified requirements
to a task-oriented workflow
with testable evidence.
Prepared for supervisor discussion

## Slide 2
HE Toolkit Dashboard
Week 4 Progress
Week 4 at a glance
Four workstreams moved the project from broad scope to evidence-backed delivery.
02
Requirements refinement
Client feedback converted into clearer must-have priorities.
Workflow design
Dashboard direction shifted toward user goals and guided task entry.
Audit and testing
Existing dashboard workflow was walked through end to end.
Evaluation planning
Volunteer user testing approach became more concrete.
Takeaway: the project direction is now clearer, more user-centred, and easier to validate.

## Slide 3
HE Toolkit Dashboard
Week 4 Progress
Requirements confirmed
Resolved decisions reduce implementation uncertainty before the next build cycle.
03
Must-have
Modelling views, model summaries, and regression plots are now treated as required functionality.
Input strategy
CSV-first upload remains the safer route because it aligns with existing HE Toolkit import functions.
Clarified
WQ/RHS handling and O:E ratio questions have been confirmed and are no longer open risks.
Effect on delivery
Less ambiguity before implementation planning.

## Slide 4
HE Toolkit Dashboard
Week 4 Progress
Task-oriented workflow direction
The design moves from technical function order to user goal-based task entry.
04
Before
Function-based tabs
Users need to understand the underlying R process before reaching useful outputs.
After
Task-based entry
Users choose the output they need; the dashboard guides inputs, checks, processing, and exports.
1
Goal
2
Inputs
3
Validation
4
Processing
5
Output

## Slide 5
HE Toolkit Dashboard
Week 4 Progress
Dashboard audit and testing findings
The existing dashboard can complete the core HE workflow, but usability risks remain.
05
Import data
RICT prediction
O:E ratio
Flow stats
Join data
HEV export
Key issues found
Raw R errors are sometimes exposed to users.
Dependency/package errors are not explained clearly.
Some failures risk leaving the app in a loading state.
Long warning messages are hard to scan.
Long calculations need clearer progress feedback.

## Slide 6
HE Toolkit Dashboard
Week 4 Progress
UI wireframe prototype
PR #8 turns the task-oriented workflow into a concrete interface for discussion.
06
PR #8
Add UI wireframe prototype
File added:
week04 UI prototype HTML
Goal Selector → HEV Workflow → Data Quality Checks
Goal Selector
Choose output first
Import Data
Biology, environment, flow, WQ, RHS
Checkpoints
Pass, warning, error states
Locked Output
Explain what blocks HEV generation
Value: provides a shared UI target before implementation starts.

## Slide 7
HE Toolkit Dashboard
Week 4 Progress
High-level test plan
PR #9 makes the new workflow testable through clear strategy and acceptance criteria.
07
PR #9
Adds the high-level dashboard test plan and optional AI-assisted analysis testing notes.
Focus: task-oriented workflow, validation, usability, and user-acceptance evidence.
Testing coverage
Functional
Negative
Boundary
Integration
Regression
Compatibility
Performance
Usability
User acceptance
Six core task areas
Prepare Data · Check Data Quality · Fill Missing Flow Data · Explore Biology-Flow Relationships · Create HEV Plot · Export Report

## Slide 8
HE Toolkit Dashboard
Week 4 Progress
User testing plan
Thomas will help recruit EA/Defra volunteers for feedback-driven refinement.
08
3-5
volunteers per round
Recruit
Thomas helps identify suitable EA/Defra volunteers.
Observe
Volunteers complete representative dashboard tasks.
Collect
Feedback captures confusion, blockers, and comments.
Refine
Team updates workflow, guidance, warnings, and errors.
Purpose: validate usability for non-programming users before treating the workflow as final.

## Slide 9
HE Toolkit Dashboard
Week 4 Progress
AI scope discussion
AI is not confirmed scope; it remains a risk and decision item.
09
Concern from Thomas
AI-generated interpretation may mislead users, especially when explaining hydroecology model outputs.
This risk affects trust, scientific interpretation, and scope control.
Discussion question
Remove AI completely from scope, or keep it only as a clearly labelled optional stretch objective?

## Slide 10
HE Toolkit Dashboard
Week 4 Progress
Next steps
Turn confirmed direction into implementation tasks, test cases, and user evaluation material.
10
Draw a data dependency map separating the core workflow from optional supporting data.
Clarify the O:E ratio workflow: biology + environmental data, with WQ, RHS, and flow as supporting inputs.
Design upload templates and data-entry templates for required and optional inputs.
Prepare a warning and error rule list for client confirmation.
Create 2-3 UI prototypes so the client can compare and choose a direction.
Evaluate feasibility and quality before committing to implementation.
Supervisor discussion: confirm whether these next-week priorities are complete and correctly ordered.